## Project Sheet
Task | Dependencies | Estimated Hours | Notes | Status | Assigned To | Condition | Start Date | End Date | Priority
Website Redesign Phase 1 | None | 40 | Initial design review | Not Started | Emily Davis | Red | 2026-01-15 | 2026-02-15 | High
Database Migration | Task 1 | 30 | Migration plan approved | In Progress | Emily Davis | Yellow | 2026-02-01 | 2026-03-01 | Medium
Budget Review | Task 2 | 20 | Review budget allocations | Complete | Chris Lee | Red | 2026-03-10 | 2026-04-10 | Low
Network Security Audit | Task 3 | 50 | Security audit scheduled | In Progress | Chris Lee | Red | 2026-04-05 | 2026-05-05 | High
User Training Sessions | Task 4 | 25 | Training materials prepared | Complete | Mike Johnson | Green | 2026-05-20 | 2026-06-20 | Medium