## High Level Project Plan
Module | Task | ComponentType | Estimate (Hrs) | Justification of Estimated Hrs
Test Case Creation | Design Test Case Input UI | UI | 16 | Multiple input fields, validation, file upload, tagging
Test Case Creation | Backend API for Test Case CRUD | Backend | 12 | Persist metadata, inputs, labels
Test Case Creation | Input File Upload & Storage | Backend | 10 | XML/JSON handling, versioning
Test Case Creation | Label/Tag Management | Backend | 6 | Filtering and regression grouping
Test Case Creation | Test Case Listing & Search UI | UI | 8 | Filter by region, POD, country
Test Case Creation | DB Schema for Test Cases | DB | 6 | Normalized scalable schema
Test Case Creation | QA Validation – Test Case Creation | QA | 8 | Positive and negative testing
API Connector Master | API Connector UI | UI | 14 | Create/Edit/View connectors
API Connector Master | API Config Capture | UI | 8 | API URL, token URL, env selection
API Connector Master | Secure Credential Handling | Backend | 10 | Encryption and secrets management
API Connector Master | Token Generation Logic | Backend | 14 | OAuth/token lifecycle handling
API Connector Master | Connector Mapping to Test Case | Backend | 8 | Multiple connectors per test
API Connector Master | DB Schema for API Connectors | DB | 6 | Env-wise configuration
API Connector Master | QA – API Connector Validation | QA | 8 | Auth, env switch testing
DB Connector Master | DB Connector UI | UI | 12 | API-specific DB config
DB Connector Master | Backend DB Connectivity | Backend | 10 | Secure DB access
DB Connector Master | Connection Pooling | Backend | 10 | Performance & reliability
DB Connector Master | API–DB Mapping | Backend | 6 | One-to-many mapping
DB Connector Master | DB Schema for DB Connectors | DB | 6 | Env isolation
DB Connector Master | QA – DB Connector Validation | QA | 8 | Failure and edge cases
Test Execution | Execution Trigger UI | UI | 8 | Manual and batch execution
Test Execution | Runtime ID Generation (MsgID, UETR) | Backend | 8 | Unique per run
Test Execution | Placeholder Replacement Engine | Backend | 12 | Dynamic XML replacement
Test Execution | API Invocation Engine | Backend | 14 | Multi-connector execution
Test Execution | Response Status Validation | Backend | 6 | HTTP status validation
Test Execution | Fetch Actual Payload from DB | Backend | 10 | Payload table query
Test Execution | Payload Comparison Engine | Backend | 16 | XML diff with ignored fields
Test Execution | Intermittent Status Tracking | Backend | 12 | Transaction lifecycle
Test Execution | Execution Result UI | UI | 10 | Pass/Fail + diff view
Test Execution | QA – End-to-End Validation | QA | 14 | Multiple connectors & reruns