## API Connector Plan
Module | Task | Sub Task | Outcome | Effort (Days) | Justification
API Connector | System Analysis & Design | Understand existing framework | Clear understanding of current system | 0.5 | Avoids duplicate work and design mismatch
API Connector | System Analysis & Design | Analyze API types & patterns | Supported API types identified | 0.25 | Required for generic connector design
API Connector | System Analysis & Design | Auth mechanism analysis | Auth approach finalized | 0.5 | Authentication drives execution flow
API Connector | System Analysis & Design | Define connector architecture | High level design prepared | 0.5 | Prevents rework during development
API Connector | Core Connector Development | Base connector implementation | Reusable API execution layer | 0.75 | Foundation of API execution
API Connector | Core Connector Development | HTTP methods support | GET/POST/PUT/DELETE supported | 0.75 | Mandatory for real APIs
API Connector | Core Connector Development | Header & parameter handling | Dynamic request support | 0.5 | Needed for flexible execution
API Connector | Auth & Token Handling | Basic & API key auth | Multiple auth types supported | 0.5 | Common enterprise usage
API Connector | Auth & Token Handling | Token generation logic | Token based auth working | 0.75 | Most APIs use token auth
API Connector | Auth & Token Handling | Token refresh & reuse | Stable executions | 0.5 | Avoids token expiry failures
API Connector | UI Configuration | API configuration screen | User friendly configuration UI | 0.75 | Improves usability
API Connector | UI Configuration | Auth & payload mapping UI | Easy mapping | 0.75 | Avoids manual setup errors
API Connector | Payload Handling | JSON payload support | Dynamic payload execution | 0.5 | Industry standard payload
API Connector | Payload Handling | Data driven variables | Reusable test cases | 0.75 | Supports multiple scenarios
API Connector | Response Validation | Status & schema validation | Accurate result validation | 1 | Ensures API correctness
API Connector | Response Validation | Response extraction | Data available for chaining | 0.75 | Needed for end-to-end flows
API Connector | Testing & QA | Unit & integration testing | Stable connector | 1 | Prevents regression
API Connector | Testing & QA | Functional execution | Validated functionality | 1 | Ensures readiness
API Connector | Bug Fixing & Stabilization | Defect fixing | Stable build | 1 | Normal stabilization phase
API Connector | Bug Fixing & Stabilization | Regression & final signoff | Release ready module | 1 | Mandatory before delivery